## Sheet1
Name | Leyen Qian
Project Team | BI Inc #1
Date
Task | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | Week Total
Lecture | 1.4 | [6 empty] | 1.4
Read/Study |  |  |  | 2 |  |  |  | 2
Team Meting | [7 empty] | 0
Sponsor Meeting |  |  | 1 |  |  |  |  | 1
TA Meeting |  | 1 | [5 empty] | 1
Implement 6 use cases with Redis TimeSeries | 2 |  |  |  | 2 | 2 | 2 | 8
0
0
0
Daily Total | 3.4 | 1 | 1 | 2 | 2 | 2 | 2 | 13.4
Work is tracked in hours spent.
Total hours per week should be 12-16.
Tasks align with the project plan
Tasks will appear and fall off with each successive week
Fill this sheet out each week - keep for your records and submit a copy to your TA
If you are spending more than about 10 minutes per week filling this out, you are probably overthinking it
It is intended both as an accountability tool and as validation for your estimates